## Sheet1
Task Name | Amount of Work | Amount Unit | Productivity Rate | Productivity Unit | Effort (hr) | Effort/Duration per 1 HC (days) | Resources | Duration (days) | Rounded Duration (days) | Actual
equation used |  |  |  |  | amount of work / productivity rate | effort (hr)/8 -- only for effort in hrs |  | effort (days) / Resources | CEILING(Duration) | due to resource leveling
Project Plan
Write Plan | 72 | pages | 3 | pages/hr | 24 | 3 | 1 | 3 | 3
Review Plan
Preparation for review | 72 | pages | 5 | pages/hr | 14.4 | 1.8 | 1 | 1.8 | 2
Review Meeting | 72 | pages | 10 | pages/hr | 7.2 | 0.9 | 1 | 0.9 | 1
Rework | 92 | defects | 3 | defects/hr | 30.6667 | 3.8333 | 1 | 3.8333 | 4
Requirements
Write requirements | 287 | req | 4 | req/hr | 71.75 | 8.9688 | 3 | 2.9896 | 3
Review Requirements
Preparation for review | 287 | req | 5 | req/hr | 57.4 | 7.175 | 1 | 7.175 | 8
Review Meeting | 287 | req | 10 | req/hr | 28.7 | 3.5875 | 1 | 3.5875 | 4
Rework | 267 | defects | 8 | defects/hr | 33.375 | 4.1719 | 3 | 1.3906 | 2
Lab and Environment Setup
Hardware
Install Server | 12 | servers | 1 | servers/day | 12 | 12 | 3 | 4 | 4
Install Clients | 28 | clients | 6 | clients/day | 4.6667 | 4.6667 | 3 | 1.5556 | 2
Software
Install Development Tools | 12 | tools | 5 | tools/hr | 2.4 | 0.3 | 3 | 0.1 | 1
Install Testing Tools | 12 | tools | 2 | tools/hr | 6 | 0.75 | 3 | 0.25 | 1
Analysis/Design Document
Write DD | 189 | pages | 5 | pages/hr | 37.8 | 4.725 | 4 | 1.1812 | 2
Review DD
Preparation for DD | 189 | pages | 5 | pages/hr | 37.8 | 4.725 | 1 | 4.725 | 5
Review Meeting | 189 | pages | 10 | pages/hr | 18.9 | 2.3625 | 1 | 2.3625 | 3
Rework | 256 | defects | 7 | defects/hr | 36.5714 | 4.5714 | 4 | 1.1429 | 2
Data Model
Create Data Model | 62 | pages | 1 | pages/hr | 62 | 7.75 | 8 | 0.96875 | 1
Review Data Model
Preparation for DM | 62 | pages | 4 | pages/hr | 15.5 | 1.9375 | 1 | 1.9375 | 2
Review Meeting | 62 | pages | 8 | pages/hr | 7.75 | 0.96875 | 1 | 0.96875 | 1
Rework | 102 | defects | 4 | defects/hr | 25.5 | 3.1875 | 8 | 0.39844 | 1
Coding and unit test
Write Code | 5890 | SLOC | 5 | SLOC/hr | 1178 | 147.25 | 13 | 11.3269 | 12
Unit Testing
Prepare/Execute Test Cases | 423 | test cases | 5 | test cases/hr | 84.6 | 10.575 | 11 | 0.96136 | 1 | 2
Fix Found Defects | 284 | defects | 5 | defects/day | 56.8 | 56.8 | 14 | 4.0571 | 5 | 8
Test Fixed Defects | 284 | defects | 5 | defects/day | 56.8 | 56.8 | 14 | 4.0571 | 5 | 6
Code Inspection
Preparation for Code Inspection | 5890 | SLOC | 125 | SLOC/hr | 47.12 | 5.89 | 1 | 5.89 | 6
Code Inspection Meeting | 5890 | SLOC | 200 | SLOC/hr | 29.45 | 3.6812 | 1 | 3.6812 | 4
Rework | 412 | defects | 3 | defects/hr | 137.3333 | 17.1667 | 13 | 1.3205 | 2
Testing
Write test plan (TP) | 289 | pages | 5 | pages/day | 57.8 | 57.8 | 12 | 4.8167 | 5 | 10
Review TP
Preparation for TP | 289 | pages | 2 | pages/hr | 144.5 | 18.0625 | 1 | 18.0625 | 19
Review TP Meeting | 289 | pages | 6 | pages/hr | 48.1667 | 6.0208 | 1 | 6.0208 | 7
Rework | 113 | defects | 5 | defects/hr | 22.6 | 2.825 | 12 | 0.23542 | 1
Execute TP (test cases) | 310 | test cases | 5 | test cases/day | 62 | 62 | 13 | 4.7692 | 5
Fix Found Defects | 179 | defects | 8 | defects/day | 22.375 | 22.375 | 13 | 1.7212 | 2
Documentation
User Documentation | 241 | pages | 5 | pages/hr | 48.2 | 6.025 | 8 | 0.75313 | 1
Review UD
Preparation for UD Review | 241 | pages | 5 | pages/hr | 48.2 | 6.025 | 1 | 6.025 | 7
Review UD Meeting | 241 | pages | 8 | pages/hr | 30.125 | 3.7656 | 1 | 3.7656 | 4
Rework | 359 | defects | 15 | defects/hr | 23.9333 | 2.9917 | 8 | 0.37396 | 1